## Executive Summary
SEC-47 SOC 2 Audit Concern Report
Sprinto audit: 2026 - SOC2 Audit
Overall conclusion | No failed/rejected statuses were found, but 22 of 443 evidence mappings remain pending across 9 unique controls. These should be closed before auditor review to reduce risk of requests or exceptions.
Audit URL | https://app.sprinto.com/app/admin/audits/840b09b2-88b8-450d-9147-2d68f70f8bf2?tab=evidence&evidenceFilters=%7B%7D&evidenceFiltersCount=0
Extracted at | 2026-06-05 11:28:52 PDT
Metric | Value | Comment
Evidence tab controls | 88 | Visible Sprinto evidence tab count
Ready for audit controls | 88 | All visible controls were marked Ready for audit
Information requested | 0 | No information-requested status visible
Review completed | 0 | No rows had completed auditor review yet
Control mapping rows reviewed | 171 | Rows in ControlMappingFile.csv
Evidence required | 443 | Aggregate from ControlMappingFile.csv
Evidence met | 421 | Aggregate from ControlMappingFile.csv
Evidence pending | 22 | Aggregate from ControlMappingFile.csv
Pending evidence rate | 5.0% | Pending / required evidence mappings
Unique controls with pending evidence | 9 | Grouped by SDC control number
High severity controls | 3 | At least one mapped criteria row has 0 completed evidence or the UI shows 1/1 incomplete
Medium severity controls | 6 | Partially evidenced controls with one incomplete evidence set
Areas affected | CC4: 5; CC7: 5; A1: 5; CC1: 3; CC5: 2; CC6: 1; C1: 1 | Pending mapping rows by SOC 2 area code
Immediate priorities | SDC 23 Internal Audit using Sprinto; SDC 60 Testing for Reliability and Integrity; SDC 97 Testing | These have 1/1 incomplete UI evidence or mapped criteria rows with zero completed evidence.
Next audit action | Resolve pending evidence, rerun ControlMappingFile.csv, and confirm Evidence pending (Count) is 0. | Evidence export itself requires email delivery and was not directly inspectable in-browser.

## Unique Control Risks
Unique Control Risks
One row per SDC control with pending evidence.
Severity | Control Number | Requirement | UI Evidence Completion | UI Status | Mapped Criteria | Area Codes | Pending Mapping Rows | Zero-Completed Mappings | Why Concerning | Recommended Remediation | Control Statement
Medium | 9 | SDC 9: Performance Review | 1/3 incomplete | Ready for audit | CC1.5 | CC1 | 1 | 0 | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity requires that all employees in client serving, IT, Engineering, and Information Security roles are periodically evaluated regarding their job responsibilities.
High | 23 | SDC 23: Internal Audit using Sprinto | 1/1 incomplete | Ready for audit | CC4.1, CC4.2, CC5.2, CC7.3, CC7.4 | CC4, CC5, CC7 | 5 | 5 | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity uses Sprinto, a continuous monitoring system, to track and report the health of the information security program to the Information Security Officer and other stakeholders.
Medium | 25 | SDC 25: Periodic Review & Update of Cybersecurity & Privacy Program | 1/4 incomplete | Ready for audit | CC1.2, CC1.3, CC4.1, CC4.2, CC5.2 | CC1, CC4, CC5 | 5 | 0 | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity's Senior Management reviews and approves the state of the Information Security program including policies, standards, and procedures, at planned intervals or if significant changes occur to ensure their continuing suitability, adequacy, and effectiveness.
Medium | 49 | SDC 49: Encrypting Data At Rest | 1/5 incomplete | Ready for audit | C1.1, CC6.7 | C1, CC6 | 2 | 0 | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity has set up cryptographic mechanisms to encrypt all production database[s] that store customer data at rest.
Medium | 59 | SDC 59: Data Backups | 1/6 incomplete | Ready for audit | A1.2 | A1 | 1 | 0 | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity backs up relevant user and system data regularly to meet recovery time and recovery point objectives and verifies the integrity of these backups.
High | 60 | SDC 60: Testing for Reliability and Integrity | 1/1 incomplete | Ready for audit | A1.2, A1.3 | A1 | 2 | 2 | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity tests backup information periodically to verify media reliability and information integrity.
Medium | 62 | SDC 62: Capacity & Performance Management | 1/7 incomplete | Ready for audit | A1.1, CC7.1, CC7.2, CC7.3 | A1, CC7 | 4 | 0 | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity has set up methods to continuously monitor critical assets to generate capacity alerts to ensure optimal performance, meet future capacity requirements, and protect against denial-of-service attacks.
High | 97 | SDC 97: Testing | 1/1 incomplete | Ready for audit | A1.3 | A1 | 1 | 1 | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity has procedures to conduct regular tests and exercises that determine the effectiveness and readiness to execute the contingency plan.
Medium | 389 | SDC 389: Updates During Installations / Removals | 1/3 incomplete | Ready for audit | CC4.1 | CC4 | 1 | 0 | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Entity periodically updates and reviews the inventory of systems as a part of installations, removals, and system updates.

## Finding Detail
Finding Detail
Mapping-level rows with Evidence pending (Count) greater than 0.
Finding ID | Severity | Area Code | Area | Criteria Code | Control Number | Requirement | UI Evidence Completion | Evidence Met | Evidence Pending | Evidence Required | Control Statement | Criteria | Why Concerning | Recommended Remediation | Source
SEC47-001 | Medium | CC1 | Control Environment | CC1.5 | 9 | SDC 9: Performance Review | 1/3 incomplete | 2 | 1 | 3 | Entity requires that all employees in client serving, IT, Engineering, and Information Security roles are periodically evaluated regarding their job responsibilities. | COSO Principle 5: The entity holds individuals accountable for their internal control responsibilities in the pursuit of objectives. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-002 | Medium | CC1 | Control Environment | CC1.3 | 25 | SDC 25: Periodic Review & Update of Cybersecurity & Privacy Program | 1/4 incomplete | 3 | 1 | 4 | Entity's Senior Management reviews and approves the state of the Information Security program including policies, standards, and procedures, at planned intervals or if significant changes occur to ensure their continuing suitability, adequacy, and effectiveness. | COSO Principle 3: Management establishes, with board oversight, structures, reporting lines, and appropriate authorities and responsibilities in the pursuit of objectives. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-003 | Medium | CC1 | Control Environment | CC1.2 | 25 | SDC 25: Periodic Review & Update of Cybersecurity & Privacy Program | 1/4 incomplete | 3 | 1 | 4 | Entity's Senior Management reviews and approves the state of the Information Security program including policies, standards, and procedures, at planned intervals or if significant changes occur to ensure their continuing suitability, adequacy, and effectiveness. | COSO Principle 2: The board of directors demonstrates independence from management and exercises oversight of the development and performance of internal control. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-004 | High | CC4 | Monitoring Activities | CC4.1 | 23 | SDC 23: Internal Audit using Sprinto | 1/1 incomplete | 0 | 1 | 1 | Entity uses Sprinto, a continuous monitoring system, to track and report the health of the information security program to the Information Security Officer and other stakeholders. | COSO Principle 16: The entity selects, develops, and performs ongoing and/or separate evaluations to ascertain whether the components of internal control are present and functioning. | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-005 | Medium | CC4 | Monitoring Activities | CC4.1 | 25 | SDC 25: Periodic Review & Update of Cybersecurity & Privacy Program | 1/4 incomplete | 3 | 1 | 4 | Entity's Senior Management reviews and approves the state of the Information Security program including policies, standards, and procedures, at planned intervals or if significant changes occur to ensure their continuing suitability, adequacy, and effectiveness. | COSO Principle 16: The entity selects, develops, and performs ongoing and/or separate evaluations to ascertain whether the components of internal control are present and functioning. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-006 | Medium | CC4 | Monitoring Activities | CC4.1 | 389 | SDC 389: Updates During Installations / Removals | 1/3 incomplete | 2 | 1 | 3 | Entity periodically updates and reviews the inventory of systems as a part of installations, removals, and system updates. | COSO Principle 16: The entity selects, develops, and performs ongoing and/or separate evaluations to ascertain whether the components of internal control are present and functioning. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-007 | High | CC4 | Monitoring Activities | CC4.2 | 23 | SDC 23: Internal Audit using Sprinto | 1/1 incomplete | 0 | 1 | 1 | Entity uses Sprinto, a continuous monitoring system, to track and report the health of the information security program to the Information Security Officer and other stakeholders. | COSO Principle 17: The entity evaluates and communicates internal control deficiencies in a timely manner to those parties responsible for taking corrective action, including senior management and the board of directors, as appropriate. | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-008 | Medium | CC4 | Monitoring Activities | CC4.2 | 25 | SDC 25: Periodic Review & Update of Cybersecurity & Privacy Program | 1/4 incomplete | 3 | 1 | 4 | Entity's Senior Management reviews and approves the state of the Information Security program including policies, standards, and procedures, at planned intervals or if significant changes occur to ensure their continuing suitability, adequacy, and effectiveness. | COSO Principle 17: The entity evaluates and communicates internal control deficiencies in a timely manner to those parties responsible for taking corrective action, including senior management and the board of directors, as appropriate. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-009 | High | CC5 | Control Activities | CC5.2 | 23 | SDC 23: Internal Audit using Sprinto | 1/1 incomplete | 0 | 1 | 1 | Entity uses Sprinto, a continuous monitoring system, to track and report the health of the information security program to the Information Security Officer and other stakeholders. | COSO Principle 11: The entity also selects and develops general control activities over technology to support the achievement of objectives. | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-010 | Medium | CC5 | Control Activities | CC5.2 | 25 | SDC 25: Periodic Review & Update of Cybersecurity & Privacy Program | 1/4 incomplete | 3 | 1 | 4 | Entity's Senior Management reviews and approves the state of the Information Security program including policies, standards, and procedures, at planned intervals or if significant changes occur to ensure their continuing suitability, adequacy, and effectiveness. | COSO Principle 11: The entity also selects and develops general control activities over technology to support the achievement of objectives. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-011 | Medium | CC6 | Logical and Physical Access Controls | CC6.7 | 49 | SDC 49: Encrypting Data At Rest | 1/5 incomplete | 4 | 1 | 5 | Entity has set up cryptographic mechanisms to encrypt all production database[s] that store customer data at rest. | The entity restricts the transmission, movement, and removal of information to authorized internal and external users and processes, and protects it during transmission, movement, or removal to meet the entity's objectives. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-012 | Medium | CC7 | System Operations | CC7.1 | 62 | SDC 62: Capacity & Performance Management | 1/7 incomplete | 6 | 1 | 7 | Entity has set up methods to continuously monitor critical assets to generate capacity alerts to ensure optimal performance, meet future capacity requirements, and protect against denial-of-service attacks. | To meet its objectives, the entity uses detection and monitoring procedures to identify changes to configurations that result in new vulnerabilities and susceptibilities to newly discovered vulnerabilities. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-013 | Medium | CC7 | System Operations | CC7.2 | 62 | SDC 62: Capacity & Performance Management | 1/7 incomplete | 6 | 1 | 7 | Entity has set up methods to continuously monitor critical assets to generate capacity alerts to ensure optimal performance, meet future capacity requirements, and protect against denial-of-service attacks. | The entity monitors system components and the operation of those components for anomalies that are indicative of malicious acts, natural disasters, and errors affecting the entity's ability to meet its objectives. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-014 | Medium | CC7 | System Operations | CC7.3 | 62 | SDC 62: Capacity & Performance Management | 1/7 incomplete | 6 | 1 | 7 | Entity has set up methods to continuously monitor critical assets to generate capacity alerts to ensure optimal performance, meet future capacity requirements, and protect against denial-of-service attacks. | The entity evaluates security events to determine whether they could or have resulted in a failure of the entity to meet its objectives and takes actions to prevent or address such failures. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-015 | High | CC7 | System Operations | CC7.3 | 23 | SDC 23: Internal Audit using Sprinto | 1/1 incomplete | 0 | 1 | 1 | Entity uses Sprinto, a continuous monitoring system, to track and report the health of the information security program to the Information Security Officer and other stakeholders. | The entity evaluates security events to determine whether they could or have resulted in a failure of the entity to meet its objectives and takes actions to prevent or address such failures. | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-016 | High | CC7 | System Operations | CC7.4 | 23 | SDC 23: Internal Audit using Sprinto | 1/1 incomplete | 0 | 1 | 1 | Entity uses Sprinto, a continuous monitoring system, to track and report the health of the information security program to the Information Security Officer and other stakeholders. | The entity responds to identified security incidents by executing a defined incident response program to understand, contain, remediate, and communicate security incidents, as appropriate. | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-017 | Medium | C1 | Additional Criteria for Confidentiality | C1.1 | 49 | SDC 49: Encrypting Data At Rest | 1/5 incomplete | 4 | 1 | 5 | Entity has set up cryptographic mechanisms to encrypt all production database[s] that store customer data at rest. | The entity identifies and maintains confidential information to meet the entity's objectives related to confidentiality. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-018 | Medium | A1 | Additional Criteria for Availability | A1.2 | 59 | SDC 59: Data Backups | 1/6 incomplete | 5 | 1 | 6 | Entity backs up relevant user and system data regularly to meet recovery time and recovery point objectives and verifies the integrity of these backups. | The entity authorizes, designs, develops or acquires, implements, operates, approves, maintains, and monitors environmental protections, software, data back-up processes, and recovery infrastructure to meet its objectives. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-019 | High | A1 | Additional Criteria for Availability | A1.2 | 60 | SDC 60: Testing for Reliability and Integrity | 1/1 incomplete | 0 | 1 | 1 | Entity tests backup information periodically to verify media reliability and information integrity. | The entity authorizes, designs, develops or acquires, implements, operates, approves, maintains, and monitors environmental protections, software, data back-up processes, and recovery infrastructure to meet its objectives. | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-020 | Medium | A1 | Additional Criteria for Availability | A1.1 | 62 | SDC 62: Capacity & Performance Management | 1/7 incomplete | 6 | 1 | 7 | Entity has set up methods to continuously monitor critical assets to generate capacity alerts to ensure optimal performance, meet future capacity requirements, and protect against denial-of-service attacks. | The entity maintains, monitors, and evaluates current processing capacity and use of system components to manage capacity demand and enable additional capacity to meet its objectives. | The control is marked Ready for audit, but Sprinto still reports one incomplete evidence set; unresolved pending evidence may trigger an auditor request or exception. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-021 | High | A1 | Additional Criteria for Availability | A1.3 | 97 | SDC 97: Testing | 1/1 incomplete | 0 | 1 | 1 | Entity has procedures to conduct regular tests and exercises that determine the effectiveness and readiness to execute the contingency plan. | The entity tests recovery plan procedures supporting system recovery to meet its objectives. | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation
SEC47-022 | High | A1 | Additional Criteria for Availability | A1.3 | 60 | SDC 60: Testing for Reliability and Integrity | 1/1 incomplete | 0 | 1 | 1 | Entity tests backup information periodically to verify media reliability and information integrity. | The entity tests recovery plan procedures supporting system recovery to meet its objectives. | One or more SOC 2 criteria mappings have no completed evidence; auditors may be unable to test this control for the mapped trust criteria. | Complete/upload the pending evidence, confirm it covers every mapped criteria code, rerun the Sprinto control export, and verify Evidence pending is 0 before auditor review. | Sprinto ControlMappingFile.csv export plus evidence tab UI confirmation

## Area Summary
Area Summary
Pending evidence concentration by SOC 2 area.
Area Code | Area | Pending Mapping Rows | Unique Controls | Pending Evidence Count | Zero-Completed Mappings | Criteria Codes | Audit Concern
A1 | Additional Criteria for Availability | 5 | 4 | 5 | 3 | A1.1, A1.2, A1.3 | High concern: includes mappings with zero completed evidence.
C1 | Additional Criteria for Confidentiality | 1 | 1 | 1 | 0 | C1.1 | Medium concern: pending evidence remains despite Ready for audit status.
CC1 | Control Environment | 3 | 2 | 3 | 0 | CC1.2, CC1.3, CC1.5 | Medium concern: pending evidence remains despite Ready for audit status.
CC4 | Monitoring Activities | 5 | 3 | 5 | 2 | CC4.1, CC4.2 | High concern: includes mappings with zero completed evidence.
CC5 | Control Activities | 2 | 2 | 2 | 1 | CC5.2 | High concern: includes mappings with zero completed evidence.
CC6 | Logical and Physical Access Controls | 1 | 1 | 1 | 0 | CC6.7 | Medium concern: pending evidence remains despite Ready for audit status.
CC7 | System Operations | 5 | 2 | 5 | 2 | CC7.1, CC7.2, CC7.3, CC7.4 | High concern: includes mappings with zero completed evidence.

## Source Notes
Source Notes and Limitations
Audit reviewed | 2026 - SOC2 Audit
Audit URL | https://app.sprinto.com/app/admin/audits/840b09b2-88b8-450d-9147-2d68f70f8bf2?tab=evidence&evidenceFilters=%7B%7D&evidenceFiltersCount=0
Smooth profile | oneleet
Extracted at | 2026-06-05 11:28:52 PDT
Evidence tab count | Value
Controls | 88
Criteria's | 11
Information requested | 0
Ready for audit | 88
Review completed | 0
Control export fact | Value
Filename | ControlMappingFile.csv
Rows | 171
Evidence met total | 421
Evidence pending total | 22
Evidence required total | 443
Columns | Area Code, Area, Criteria Code, Criteria, Control Number, Control Statement, Evidence met (Count), Evidence pending (Count), Total evidence required (Count)
Limitation | Detail
Limitation | The Sprinto `Download evidences` action did not produce an immediate browser download; Smooth reported that the evidence export is emailed later, so evidence-level owners, due dates, and item names could not be verified from the downloaded file in this run.
Limitation | The audit table did not show owner, assignee, due date, or last-updated fields for the pending rows.
Limitation | No failed, rejected, Information requested, or non-Ready-for-audit statuses were visible during the Smooth review.
Interpretation note | The audit table reported 88 controls as Ready for audit. This workbook treats pending evidence counts as report-risk indicators because SOC 2 auditors may request, reject, or exception controls whose supporting evidence remains incomplete.